## DRM
<Project Title> |  | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Contractor Name (& Abbreviation ) | Construction Co. (Contractor) | Contractor Name (& Abbreviation ) | Various
Design Responsibility Matrix (DRM)
[24 empty] | Rev | Date
[24 empty] | ?? | DD/MM/YY
Colour Key | Green Items indicate CDP | [22 empty] | Comments / Notes
| Amber text indicates Fabrication / Shop Drawings | [22 empty] | 1. DRM Must be complete and agreed, and included in Contract Docs, including appointments/novations
| Grey Text Indicates Sub-Heading | [22 empty] | 2. DRM is project specific and should be developed from blank based on Project Brief & Scope
| Red Text denotes change since last revision | [22 empty] | 3. Where Client version is to be used, this must be subject to detailed review/comment, prior to acceptance,
This Schedule defines responsibility for each general aspect of the design to specific parties. It is not intended to be fully exhaustive but aims to identify and allocate responsibility for the main tasks which are to be undeertaken during the course of the Project | [23 empty] | this includes any changes to DRM during the project lifecycle 4. This Document must not be revised without agreement of Project Lead, Commercial Manager, Design Manager, Planner and acceptance to changes by all parties with Design responsibility on the Project 5. The DRM should be checked with the Regional Design Mangager, prior to Gateway 2 and Gateway 4
Employer / Contractor / Consultant Input |  | Client | Client Agent / PM | Principal Designer | BiM Manager | Architect (Lead) | Structural Engineer | Civil Engineer | M&E Engineer | Landscape Architect | Fire Engineer | Acoustician | Ecologist | LZCT / Sustainability | Interior Designer | Planning Consultant | BREEAM Consultant | Wayfinding Signage | CTM Consultant | Approved Inspector | Principal Contractor | MEP Sub-Contractor | CDP Sub Contractor
P | Denotes primary responsibility (occassionaly this may be shared)
1 | Denotes Co-Ordinated Design Intent where relevant to the pacakge
2 | Denotes denotes supporting role or contribution in task
1 | General
1.01 | Appointment of Consultants | [22 empty] | Principle Designer appointement by Client Team
1.02 | Development of brief
1.03 | Instruct changes to brief
1.04 | Site ownership and boundary locations
1.05 | DDA Requirements + Provisions
1.06 | 3D Visualisations
1.07 | BIM Information Manager
1.08 | BIM Execution Plan (BEP)
1.09 | BiM Model
1.1 | Design team management
1.11 | CDM Compliance/Risk Assessments | [22 empty] | Input to Principle Designer Risk Register by all
1.12 | Pre Construction Health & Safety Information
1.13 | Construction Phase Health & Safety Plan | [22 empty] | Input / Commentary only from Consultants
1.14 | Health & Safety File | [22 empty] | Content defined & colated by Principle Designer
1.15 | Specifications | [22 empty] | Designers Specifications by discipline / Scope
1.16 | Contract Administration
1.17 | Minutes of meetings | [22 empty] | As required and agreed - Designers Minutes limited to where no Contractor attendance (Workshops etc.)
1.18 | Certification/Valuations
1.19 | Site visits | [22 empty] | Limitations on frequency of site visits subject to agreement - VC or similar to be adopted where possible
1.2 | Cost planning and control
1.21 | Compliance with Budget | [22 empty] | All parties have a responsibility to ensure Cost implications are considered during design development
1.22 | Preparation of Snagging Lists | [22 empty] | Snagging scheduled and resolved by Contractor prior to Client Snagging / IT Inspection
1.23 | Application for Completion Certificate
1.24 | Fire Certification
1.25 | Final Construction Issue | [22 empty] | For Use in O+M Manuals - As required / defined by Principle Designer
1.26 | Energy Efficiency Evaluation and SBEM Calculations
1.27 | U-Values - Thermal Design & Air Tightness | [22 empty] | Contractor may elect to appoint a specialist Consultant to assist in this area
1.28 | Services Coordination
1.29 | Services Commissioning | [22 empty] | Appointed Sub-Co to lead with Contractor programme input
1.3 | Energy Performance Certificate (EPC) | [22 empty] | EPC provided by relevant Specialist M+E Sub, with input from wider team to meet project target EPC
1.31 | Fire Strategy
1.32 | Acoustic Strategy
1.33 | Way Finding Strategy
Entrance / Feature Signage
Statutory Signage
1.34 | BREEAM Evidence by Credit | [22 empty] | Input / Evidence to be provided on request to meet or exceed taget credits
1.35 | Strategy for access for cleaning & maintenance, including MEWP's - Building Fabric
1.36 | Strategy for access for cleaning & maintenance, including MEWP's - Building Services installations
1.37 | Accommodation Schedule
1.38 | Room Layouts / data sheets
2 | National + Local Government Departments and Agencies
2.01 | Highways
2.02 | Environment – SEPA
2.03 | Planning – Local Authority - Planning, reserved matters and conditions
2.04 | Building Regulations – Local Authority | [22 empty] | Lead varies dependant on Warrant Stage - Refer to MIDP
3 | Emergency Services
3.01 | Security Strategy
3.02 | Fire + Ambulance Management Plan
4 | Consultation or Interested Groups
4.01 | Adjacent Land Owners | [22 empty] | Client team to lead with support from Contractor
4.02 | Community Council/Local interest groups | [22 empty] | Split responsibility on this item - Client Team & Contractor lead
4.03 | Bus Operators | [22 empty] | Client team to lead
5 | Utilities
5.01 | Utilities – Negotiations, Routes, Capacities | [22 empty] | Contractor Lead on utilities with support from Appointed Sub-Co
5.02 | Utility Quotations
5.03 | Utility Orders
5.04 | Renewable Energy Sources
6 | Site + External works
6.01 | Existing site services investigation
6.02 | Schedule of condition – Delap on Roads & Highways
6.03 | Boundary Conditions including setting out | [22 empty] | S/O by Principle Contractor based on co-ordinated info from Principle Designer & Project Manager
6.04 | Ground/Soil Investigations & contamination including topographical survey | [22 empty] | Contractor to undertake as required to support Client issued info
6.05 | Landscape - Hard | [22 empty] | M+E interface on any services - eg. Lighting etc…
6.06 | External Slabs / Hardstandings / Plinths
6.07 | Landscape - Soft | [22 empty] | Final Levels / quantitiy driven by Sub-Co to be aligned with Consultant Design info
6.08 | Street Furniture, Fixtures and Fittings
6.09 | Site wide drainage – Surface and Foul
6.1 | Outfalls from site
6.11 | External Services
6.12 | Roads, Car parking, Vehicular Ramps Pathways, Road Markings, including street lighting setting out, levels, drainage falls etc. | [22 empty] | Scope / Materials / Levels by Landscape Architect - Construction Detailing from C+S Engineer
6.13 | Site formation and sub-base
6.14 | Site Wide Levels | [22 empty] | Final Levels agreed in conjunction with Sub-Co and C+S Engineer
6.15 | Swept Path analysis between roads, car park & pavements
6.16 | Incoming Services – Conenctions, Metering, Sub-Station, Tanks etc
6.17 | Disconnections, diversions & terminations of existing services
6.18 | Handrails, Balustrades and Guarding (design intent only)
6.19 | Handrails, Balustrades and Guarding (detail design)
6.21 | Protection Barriers to Service Areas
6.22 | Car park protection barriers / Bollards
6.23 | Perimeter Fencing
6.24 | Road Signage | [22 empty] | Client team interface required where outwith Site Boundary
6.25 | Public Artwork | [22 empty] | Final Comercial Allowance to form basis for scope - Subject to agreement with Client team
7 | Foundations + Under building
7.01 | Loadings (including Plant loadings)
7.02 | Foundation Design
7.03 | Re-Bar Design
7.04 | Piling
7.05 | DPM & Waterproofing
7.06 | DPC
7.07 | Retaining Structures
7.08 | Retaining Structures waterproof construction
7.09 | Slab Design including movement joints
7.1 | Lift pit structural details | [22 empty] | Min clear dimensions defined by Architect
7.11 | Coordination between Services and Drainage
7.12 | Gas Membrane System | [22 empty] | Where requried - C+S Eng to advise
7.13 | Tanking | [22 empty] | Includes Service trenching & Lift pits
7.14 | Interface between dpm and tanking
7.15 | Service entry details - waterproofing, pits, etc | [22 empty] | Locations / Size of penetrations to be co-ordinated with TUV - details /Spec by others
8 | Storm & Foul Drainage
8.01 | Existing drainage surveys (if required)
8.02 | Design and specification (below ground to top of ground bearing slab)
8.03 | Sanitary fittings | [22 empty] | Connection design by MEP Engineer / Sub-Co
8.04 | Design and Specification (above ground bearing slab)
8.05 | Storm Drainage - Flow Rates (Design Intent) | [22 empty] | Input from Specialist where required - To be arranged via Contractor
8.06 | Storm Drainage - Outlet positions / Sizing / Setting Out
8.07 | Above Ground Drainage
8.08 | Above Ground Drainage - Pop Up locations
8.09 | Foul Drainage provision at ground Slab level
8.1 | Tanks / Chambers and similar to Sub-Struct Drainage | [22 empty] | Subject to co-ord with Services design
9 | Structural Frame
9.01 | Specification | [22 empty] | Includes Corrosion protection & Loading Criteria
9.02 | Frame Design
9.03 | Temporary Bracing If Required | [22 empty] | Stability in Temp condition to be considered based on Sub-Co dequence
9.04 | Finishes to Frame
9.05 | Lintels – Performance spec / Schedule | [22 empty] | Includes both Internal & Envelope requirements
9.06 | Masonry Support Systems including wall ties, head restraints | [22 empty] | Includes both Internal & Envelope requirements
9.07 | Connection details
9.08 | Secondary Steelwork | [22 empty] | Includes Wind Posts, Framed Openings , Trimmer Steel & Head Restraint
9.09 | Structural Movement Joints
9.1 | Floor Slab Design
9.11 | Finished Floor Levels | [22 empty] | TOS & SSL by Struct Eng to suit same
9.12 | Stairs - Concrete and Metal (design intent)
9.13 | Stairs - Concrete and Metal (detailed design) | [22 empty] | PCC Stair units / Steel Stair developed As fabrication drawings from supplier
10 | Roof | [22 empty] | Comments
10.01 | Specification
10.02 | Lightweight Roof (Design Intent)
10.03 | Lightweight Roof (Detail Design)
10.04 | Concrete Roof / Terrace (Design Intent)
10.05 | Concrete Roof / Terrace (Detailed Design)
10.06 | Canopy Roofs (Intent)
10.07 | Canopy Roofs (Detailed Design) | [22 empty] | Envelope Sub-Co to provide detailed design / fabrication
10.08 | Design Loadings
10.09 | RWP / RWO & gutter design (Intent)
10.1 | RWP / RWO & gutter design (Detail Design)
10.11 | Roof Lights (Design Intent )
10.12 | Roof Lights (Detailed Design)
10.13 | Service Penetrations Co-Ordination
10.14 | Service Penetrations Detailing | [22 empty] | Architect to incorporate Manufacturers typical details & co-ordinate with services design
10.15 | Roof Access - (Design Intent)
10.16 | Roof Access - (Detailed Design)
10.17 | Bird deterrent strategy
11 | External Envelope + Wall Constructions
11.01 | Specifications
11.02 | Set-out & coordination with other Elements / Structures / MEP
11.03 | DPC / Membranes (Inc Air Integrity / permeability)
11.04 | Blockwork, Design and Specification
11.05 | Metal/other panel cladding systems (including fascias and soffits) (Design Intent)
11.06 | Metal/other panel cladding systems (including fascias and soffits) (Detail Design) | [22 empty] | M+E Input on service interface generally
11.07 | Curtain walling including doors & Windows (Design Intent)
11.08 | Curtain walling Including Doors Windows (Detailed Design)
11.09 | Louvres - design and specification (Design Intent) | [22 empty] | MEP Input limited to position and % free area requirements & impact on acoustic requiremetns to plant
11.1 | Louvres - design and specification (Detailed Design) | [22 empty] | Refer also to secondary steel and support (Section 9, above)
11.11 | Smoke extract - design and specification (design intent)
11.12 | Smoke extract - design and specification (detailed design)
11.13 | External Doors, including automatic/roller shutter doors - details & ironmongery (Design Intent) | [22 empty] | Refer also to secondary steel and support (Section 9, above)
11.14 | External Doors, including automatic/roller shutter doors - details & ironmongery (Detailed Design) | [22 empty] | Refer also to secondary steel and support (Section 9, above)
11.15 | SFS & Lining (DesiIgn intent)
11.16 | SFS & Lining (Detailed Design)
11.17 | Render Systems
11.18 | Specialist Render Systems | [22 empty] | Specialist input on Specification & Standard detials
11.19 | Mastic Specification
11.2 | External envelope – access for cleaning & maintenance, including BMU (Design intent)
11.21 | External envelope – access for cleaning & maintenance, including BMU (detailed design) | [22 empty] | Individual Sub-Co to incorporate requiremetns of M+A in relevant WP
12 | Internal Walls + Finishes
12.01 | Ceilings – specification
12.02 | Ceilings - Typical Details
12.03 | Ceilings - Reflected Ceiling Plans
12.04 | Partitions & Dry Lining - Specification
12.05 | Partitions & Dry Lining - Typical Details
12.06 | Partitions & Dry Lining - S/O
12.07 | Folding Partitions (Design Intent) | [22 empty] | M+E Design interface above and for operation
12.08 | Folding Partitions (Detailed Design) | [22 empty] | Refer also to secondary steel and support (Section 9, above)
12.09 | IPS including vanity units (Design Intent )
12.1 | IPS vanity units (detailed design) | [22 empty] | Struct Engineer to review any loading / sub frame suitablilty only
12.11 | Internal Roller shutters (Design Intent) | [22 empty] | M+E Design interface for operation and alarms
12.12 | Internal Roller shutters (detailed design) | [22 empty] | Refer also to secondary steel and support (Section 9, above)
12.13 | Floor screeds – Structural
12.14 | Floor screeds – Levelling Screed | [22 empty] | As required to meet tolerances fo floor finish
12.15 | Slab recesses - Kitchens, CDU, Matt wells , Showers, U-Floor Heating etc
12.16 | Internal Doors/screens | [22 empty] | Refer also to secondary steel and support (Section 9, above)
12.17 | Internal Doors/screens - Fabrication Drawings
12.18 | Ironmongery Schedule (Design Intent)
12.19 | Ironmongery Schedule (Detail Design) | [22 empty] | Manufacturers design provided based on Construction Design info - Suiiting and Access strategy by End User
12.2 | Joinery, Architraves and Skirtings
12.21 | Bespoke Joinery (Design Intent)
12.22 | Bespoke Joinery ( Detailed Design) | [22 empty] | Fabrication design or similar to be developed for approval in line with design itent by Specialist
12.23 | Internal finishes schedule
12.24 | BWICS
12.25 | Lift Finishes(Design Intent )
12.26 | Lift Finishes (detailed design) | [22 empty] | Lift Manufacturer to provide detailed design based on Design Intent
12.27 | FF+E (Design intent) | [22 empty] | Equipment schedule developed and agreed with Client team
12.28 | FF+E (Detailed Design / Fabrication)
12.29 | Acoustic Measures
13 | Fire Protection
13.01 | Requirement for structural fire protection
13.02 | Fire protection - board or intumescent, fire Stopping and fire Barriers (Design Intent)
13.03 | Fire protection - board or Intumescent, fire stopping and fire barriers (Detail Design) | [22 empty] | Sub-Co systems / Spec to be incorporated to design where required
13.04 | Fire Hydrants
13.05 | Fire Shutters and Smoke Curtains (Design Intent including any Secondary Steelwork)
13.06 | Fire Shutters and Smoke Curtains (Detailed Design including any Secondary Steelwork)
13.07 | Fire Detection + Alarm Systems
13.08 | Emergency Lighting + Fire Signage (illuminated)
13.09 | Fire & Statutory Signage (Non illuminated)
13.1 | Sprinkler Systems (Design Intent Only)
13.11 | Sprinkler Systems (Detailed Design)
13.12 | Fire Extinguishers
14 | M&E
14.01 | Mains Water supply
14.02 | Hot + Cold Water Supply & distribution including insulation
14.03 | Specifications for all M&E equipment
14.04 | Electrical services
14.05 | Builders-work schedules
14.06 | Service Interfaces with other Elements
14.07 | Heating System
14.08 | Fuel type and supply
14.09 | Lightning Protection
14.1 | External building & environment lighting
14.11 | Internal Feature Lighting
14.12 | External Feature Lighting
14.13 | Building management systems
14.14 | Passenger Lifts (Design Intent)
14.15 | Passenger Lifts (Detailed Design)
14.16 | Acoustic Design + treatment of plant in relation to services
14.17 | Vibration control in connection with M+E services
14.18 | IT Hub rooms
14.19 | Service Trenches
14.2 | Audio Loops
14.21 | Ventilation and A/C systems
14.22 | Access Control
14.23 | Alarms & Detection Systems
14.24 | Medical Gas Instalaltions
14.25 | PV Array
14.26 | Services brackets and supports
14.27 | Conduit sizes and routes
14.28 | Earthing and associated arrays and farms
14.29 | Audio visual systems
14.3 | Vehicle Charge Points
14.31 | WiFi heat mapping simulation and analysis
15 | Architectural/General Metalwork
15.01 | Handrails, Balustrades and Guarding (design intent)
15.02 | Handrails, Balustrades and Guarding (detailed design)
15.03 | Glazed Balustrades and Guarding Systems (design intent)
15.04 | Glazed Balustrades and Guarding Systems (detailed design)
15.05 | Service Access, Walkways and Stairs etc. (design intent)
15.06 | Service Access, Walkways and Stairs etc. (detail design)
15.07 | Plant Screen (Design Intent)
15.08 | Plant Screen (Detailed Design)
15.1 | Mansafe Systems (Design Intent)
15.11 | Mansafe Systems (Detailed Design)
16 | MISCELLANEOUS
16.01 | Refuse Equipment
16.03 | Client Fit-Out | [22 empty] | Scope to be defined - Consultant input limited to Design Intent
16.04 | Kitchen fit out / Catering Design | [22 empty] | Kitchen Fit-Out shell and core - Speciailist Fit Out to be co-ordinated with Layouts & Building Services
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update Document to reflect Project Specific Naming Convention where required